## Project Plan
Jumpy Street
Project Lead:
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
Play a bunch of crossy road | Week .25 | All | Not Implemented
Making Movement/Object grid | Week .5 |  | Not Implemented
The creation of a Main menu with instructions and credits screen. | Week .5 |  | Not Implemented
The ability for the charcter to move in cardinal directions and Jump (Camera is vertically fixed on player | Week 1 |  | Not Implemented
Importing all assets | Week 1 |  | Not Implemented
Controller that feeds in safe and hazardous zones and deletes old ones. ("Waterfall" zone of oncoming safe and hazerdous zones.) | Week 1.5 |  | Not Implemented
Implementation of impassable zones on either side of the terrain. | Week 1.5 |  | Not Implemented
The procedural creation of platforms for the character to navigate in a sequential fashion. | Week 2 |  | Not Implemented
The ability for the player to jump between platforms or safe zones. | Week 2.5 |  | Not Implemented
Death zones that are on the front of obstacles to be avoided or in zones to be crossed. | Week 3 |  | Not Implemented
Implemetation of obstacles and dead zones | Week 3 |  | Not Implemented
The creation of a UI system that keeps track of the player score and high scores. | Week 4 |  | Not Implemented
Blockers on safe zones | Week 5 |  | Not Implemented
Player able to go back and forth from opposite sides | Week 5.5 |  | Not Implemented
Different Biomes | Week 6 |  | Not Implemented
System to punish idleness | Week 6 |  | Not Implemented
Experiment with camera angles | Week 6 |  | Not Implemented
Insert a row above to add more features to the list.