## Project Plan
Jumpy Street
Project Lead: Brennan Sullivan and Jacob Coleman
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
Play a bunch of crossy road | Week .25 | All | In Progress
Making Movement/Object grid | Week .5 | Jacob | Done
The creation of a Main menu with instructions and credits screen. Also start UI creation for level. | Week .5 | Brennan | Done
The ability for the charcter to move/jump in cardinal directions (Camera is vertically fixed on player | Week 1 | Brennan | Not Implemented
Importing all assets | Week 1 | Jacob | In Progress
Controller that feeds in safe and hazardous zones and deletes old ones. ("Waterfall" zone of oncoming safe and hazerdous zones.) | Week 1.5 | Jacob | In Progress
Implementation of impassable zones on either side of the terrain. | Week 1.5 | Brennan | In Progress
Adding capability for controller to spawn object in hazardous zones and safe zones. | Week 2 | Brennan | Not Implemented
The ability for the player to jump between platforms or safe zones. | Week 2.5 | Jacob | Not Implemented
Death zones that are attached to objects | Week 3 | Jacob | Not Implemented
Implemetation of obstacles and dead zones to cross | Week 3 | Brennan | Not Implemented
The creation of a UI system that keeps track of the player score and high scores. | Week 4 | Both? | Not Implemented
Blockers on safe zones | Week 5 | Jacob | Not Implemented
Player able to go back and forth from opposite sides | Week 5.5 | Brennan | Not Implemented
Different Biomes | Week 6 | Brennan | Not Implemented
System to punish idleness | Week 6 | Jacob | Not Implemented
Experiment with camera angles | Week 6 | Both? | Not Implemented
Insert a row above to add more features to the list.